## Sheet1
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
1 | Not understanding method or topic when learning | Working for too long may induce strain injury | Pay attention in class, follow along and ask questions if something is not clear | Always ask questions if you are confused, work outside learning hours and watch back recorded videos to understand better | Likely | Major | 12
2 | Risk Of getting hacked | Working on a network that may be unsecure | If my project is hacked, information leak can be very risky and could cause long term damage to others or the company. | Use SSH and other encryption methods such as adding password to files. Never connect to unsecure or public networks or upload secret keys to github. | Possible | Major | 8
3 | Not starting the project on time | leaving the project till the last minute | Failing to start the project on time could lead to work not being up to standard and vital information could be left out | Work outside of learning hours for 1/2 hours a day to work gradually. | possible | Severe | 10
4 | Eye strain | Working for too long may induce strain injury | Take regular breaks and blink more | Maintain a reasonable level of comfort while working | Expected | Minimal | 4
5 | Muscle injuries - Shoulder and back | bad posture and mouse rotation can cause these problems | Get up and move around every now and again | Arrange seating position, rest often and don’t over work/ exercise regularly | Expected | Minimal | 4
6 | System Malfunction | If the computer breaks down due to overheating or other problems, the website would not run as the server would be offline | Try and restart the computer or run in safe mode | Always have a backup machine ready with backup data stored maybe via cloud in order to get the server back up and running | Possible | Severe | 10
SEVERITY
|  |  | Minimal | Minor | Moderate | Major | Severe
| LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
|  | Expected | 4 | 8 | 12 | 16 | 20
|  | Likely | 3 | 6 | 9 | 12 | 15
|  | Possible | 2 | 4 | 6 | 8 | 10
|  | Unlikely | 1 | 2 | 3 | 4 | 5